## Dashboard
HWR Berlin — International Business Management
Application & Relocation Tracker ¦ Target intake: October 2027
Today's date: | 2026-08-31
Target application submission: | 2027-06-01
Days remaining: | 274
Total Tasks | Completed | In Progress | Blocked | Not Started | % Complete | Status | Count
30 | 0 | 0 | 0 | 30 | 0% | Done | 0
[6 empty] | In Progress | 0
[6 empty] | Blocked | 0
[6 empty] | Not Started | 30
Overall Progress | 0%
Progress by Category
Category | Total | Done | % Done
Documents & Transcripts | 5 | 0 | 0%
German Language | 3 | 0 | 0%
English Proof | 4 | 0 | 0%
uni-assist Application | 6 | 0 | 0%
HWR Application | 6 | 0 | 0%
Visa & Relocation | 5 | 0 | 0%
Spouse / Family | 1 | 0 | 0%

## Master Tracker
Master Task Tracker
Update the Status column (dropdown) as you progress. Dashboard updates automatically.
Phase | Task | Category | Start Date | Target Date | Status | Priority | % Done | Notes
Phase 1: Sep-Dec 2026 | Request Nnamdi Azikiwe University transcript | Documents & Transcripts | 2026-09-01 | 2026-10-15 | Not Started | High | 0%
Phase 1: Sep-Dec 2026 | Locate WAEC/NECO certificate & results | Documents & Transcripts | 2026-09-01 | 2026-09-30 | Not Started | High | 0%
Phase 1: Sep-Dec 2026 | Request BYU-Pathway certificate & academic record | Documents & Transcripts | 2026-09-01 | 2026-10-15 | Not Started | High | 0%
Phase 1: Sep-Dec 2026 | Request BYU-Idaho official transcript | Documents & Transcripts | 2026-09-01 | 2026-10-15 | Not Started | High | 0%
Phase 1: Sep-Dec 2026 | Gather passport & CV | Documents & Transcripts | 2026-09-01 | 2026-09-15 | Not Started | Medium | 0%
Phase 1: Sep-Dec 2026 | Create uni-assist account | uni-assist Application | 2026-09-15 | 2026-10-01 | Not Started | High | 0%
Phase 1: Sep-Dec 2026 | Enter Nnamdi Azikiwe University in uni-assist | uni-assist Application | 2026-10-01 | 2026-10-31 | Not Started | Medium | 0%
Phase 1: Sep-Dec 2026 | Enter BYU-Pathway in uni-assist | uni-assist Application | 2026-10-01 | 2026-10-31 | Not Started | Medium | 0%
Phase 1: Sep-Dec 2026 | Enter BYU-Idaho credits in uni-assist | uni-assist Application | 2026-10-01 | 2026-10-31 | Not Started | Medium | 0%
Phase 1: Sep-Dec 2026 | Start German course toward A1 | German Language | 2026-09-01 | 2026-12-31 | Not Started | High | 0%
Phase 1: Sep-Dec 2026 | Confirm HWR entrance eligibility route (uni-assist evaluation) | uni-assist Application | 2026-11-01 | 2026-12-15 | Not Started | High | 0%
Phase 2: Jan-Mar 2027 | Reach German A2 | German Language | 2027-01-01 | 2027-03-31 | Not Started | High | 0%
Phase 2: Jan-Mar 2027 | Verify HWR's exact English B2 evidence policy | English Proof | 2027-01-01 | 2027-01-31 | Not Started | High | 0%
Phase 2: Jan-Mar 2027 | Register for IELTS | English Proof | 2027-01-15 | 2027-02-15 | Not Started | Medium | 0%
Phase 2: Jan-Mar 2027 | Sit IELTS exam (target 6.0-6.5) | English Proof | 2027-02-15 | 2027-03-15 | Not Started | High | 0%
Phase 2: Jan-Mar 2027 | Receive IELTS results | English Proof | 2027-03-15 | 2027-03-31 | Not Started | Medium | 0%
Phase 3: Apr-May 2027 | Compile full document folder (all originals + copies) | HWR Application | 2027-04-01 | 2027-04-30 | Not Started | High | 0%
Phase 3: Apr-May 2027 | Get certified translations where required | HWR Application | 2027-04-01 | 2027-04-30 | Not Started | Medium | 0%
Phase 3: Apr-May 2027 | Draft motivation letter (entrepreneurship -> tech -> IBM narrative) | HWR Application | 2027-04-01 | 2027-04-30 | Not Started | Medium | 0%
Phase 3: Apr-May 2027 | Reach German B1 (stretch goal) | German Language | 2027-04-01 | 2027-06-30 | Not Started | Low | 0%
Phase 3: Apr-May 2027 | Final review of uni-assist profile before submission window | uni-assist Application | 2027-05-01 | 2027-05-31 | Not Started | High | 0%
Phase 4: Jun-Jul 2027 | Submit uni-assist / HWR application | HWR Application | 2027-06-01 | 2027-06-01 | Not Started | High | 0%
Phase 4: Jun-Jul 2027 | Respond to any uni-assist document requests | HWR Application | 2027-06-01 | 2027-07-15 | Not Started | Medium | 0%
Phase 4: Jun-Jul 2027 | Track application status until decision | HWR Application | 2027-06-01 | 2027-08-31 | Not Started | Medium | 0%
Phase 5: Post-Admission | Receive admission letter | Visa & Relocation | 2027-08-01 | 2027-08-31 | Not Started | High | 0%
Phase 5: Post-Admission | Arrange proof of financial resources (blocked account) | Visa & Relocation | 2027-08-01 | 2027-09-15 | Not Started | High | 0%
Phase 5: Post-Admission | Obtain German health insurance | Visa & Relocation | 2027-08-15 | 2027-09-15 | Not Started | Medium | 0%
Phase 5: Post-Admission | Apply for German student visa | Visa & Relocation | 2027-09-01 | 2027-09-30 | Not Started | High | 0%
Phase 5: Post-Admission | Arrange accommodation in Berlin | Visa & Relocation | 2027-08-15 | 2027-09-30 | Not Started | Medium | 0%
Phase 5: Post-Admission | Plan wife's dependent / family reunification visa | Spouse / Family | 2027-08-15 | 2027-10-15 | Not Started | High | 0%

## Documents Checklist
Document Checklist
Every item uni-assist / HWR may request. Mark Status as you obtain each.
Document | Required For | Status | Priority | Notes
Passport (valid, with copies) | uni-assist, Visa | Not Obtained | High
WAEC/NECO certificate & results | uni-assist entrance evaluation | Not Obtained | High
Nnamdi Azikiwe University transcript | uni-assist entrance evaluation | Not Obtained | High | 1 year completed
Nnamdi Azikiwe University admission letter (if available) | uni-assist entrance evaluation | Not Obtained | Medium
BYU-Pathway certificate | uni-assist entrance evaluation | Not Obtained | High
BYU-Pathway academic record | uni-assist entrance evaluation | Not Obtained | High
BYU-Idaho official transcript | uni-assist entrance evaluation | Not Obtained | High | Credits earned, degree not completed
BYU-Idaho admission evidence | uni-assist entrance evaluation | Not Obtained | Medium
CV / resume | uni-assist, HWR | Not Obtained | Medium
Motivation letter | HWR application | Not Obtained | Medium | Entrepreneurship -> tech -> IBM narrative
German language certificate (A2 minimum) | HWR application | Not Obtained | High | Target B1 before travel
English B2 proof (IELTS/TOEFL or equivalent) | HWR application | Not Obtained | High | Confirm exact HWR policy first
Certified translations of non-English/German documents | uni-assist, HWR | Not Obtained | Medium
Admission letter from HWR | Visa application | Not Obtained | High | Issued after acceptance
Proof of financial resources (blocked account) | Visa application | Not Obtained | High
German health insurance confirmation | Visa application | Not Obtained | Medium
Accommodation confirmation in Berlin | Visa application | Not Obtained | Medium
Marriage certificate | Spouse dependent visa | Not Obtained | High
Spouse's passport & documents | Spouse dependent visa | Not Obtained | High
Documents Obtained: | 0 / 19

## Language Progress
Language Progress Tracker
German A2 minimum required by HWR; English B2 required. Track milestones here.
Language | Milestone | Target Date | Achieved Date | Status | Notes
German | A1 | 2026-12-31 |  | Not Started
German | A2 (HWR minimum) | 2027-03-31 |  | Not Started | Required for admission
German | B1 (recommended) | 2027-06-30 |  | Not Started | Stretch goal before travel
English | Confirm HWR's exact B2 evidence policy | 2027-01-31 |  | Not Started
English | IELTS registration | 2027-02-15 |  | Not Started
English | IELTS exam sat | 2027-03-15 |  | Not Started | Target score 6.0-6.5
English | IELTS results received | 2027-03-31 |  | Not Started

## Key Dates
Key Dates & Deadlines
Milestone | Date | Days Remaining | Notes
German A1 target | 2026-12-31 | 122 | Language school / self-study milestone
German A2 target (HWR minimum) | 2027-03-31 | 212 | Required by HWR
IELTS exam window | 2027-03-15 | 196 | Target score 6.0-6.5
Document folder complete | 2027-04-30 | 242 | All originals, copies & translations ready
German B1 stretch target | 2027-06-30 | 303 | Recommended, not required
HWR/uni-assist application window opens | 2027-06-01 | 274 | Official window: 1 Jun - 15 Jul
Personal submission deadline | 2027-06-01 | 274 | Submit early, don't wait for 15 Jul
Official application deadline | 2027-07-15 | 318 | Hard deadline for winter semester
Expected admission decision | 2027-08-31 | 365 | Estimate — confirm with HWR
Student visa application | 2027-09-30 | 395 | After admission letter received
Target arrival in Berlin | 2027-10-01 | 396 | Before October 2027 intake
Formulas:
Days Remaining = [Date]-TODAY()